Sprint Planning - Flousy Project

Agile Planning Document - Week 1

Student name: MERYEM ZAGUI

Course: Agile Project Management

Methodology: Scrum - 4 sprints of 2 weeks

# Table of Contents

Right-click the table of contents and choose "Update Field" to refresh page numbers.

Table of Contents	1

1. Introduction	1

2. Project Vision and Objectives	1

2.1 Vision Statement	1

2.2 SMART Objectives	1

2.3 Project Scope	1

Included in scope	1

Excluded from scope (out of scope for V1)	1

2.4 Added Value for Users	1

3. Project Roadmap	1

3.1 Key Milestones	1

3.2 Textual Diagram of the Roadmap	1

4. Product Backlog and User Stories	1

4.1 Prioritisation Method: MoSCoW	1

4.2 Product Backlog	1

4.3 Acceptance Criteria of the Three Most Important Stories	1

US-01 - Manual transaction entry (Must, 5 points)	1

US-05 - Budget overrun alert (Must, 8 points)	1

US-07 - Savings goal creation (Must, 5 points)	1

5. Task Breakdown	1

5.1 US-01 - Manual Transaction Entry (total: 24 hours)	1

5.2 US-02 - Transaction List (total: 12 hours)	1

5.3 US-03 - Expense Categorisation (total: 16 hours)	1

6. Sprint 1 Planning	1

6.1 Sprint Goal	1

6.2 Sprint Backlog	1

6.3 Team Capacity	1

6.4 Day-by-Day Timeline (5 - 16 January 2026)	1

6.5 Scrum Ceremonies During the Sprint	1

7. Risk Analysis	1

7.1 Explanation of the Mitigation Strategies	1

7.2 Continuous Risk Monitoring	1

8. Stakeholder Expectations	1

8.1 Power / Interest Matrix	1

8.2 Communication Strategy	1

9. Conclusion	1

10. Appendices	1

Appendix A - Burndown Chart Model (Sprint 1)	1

Appendix B - Daily Stand-up Template	1

Appendix C - Definition of Done (DoD)	1

# 1. Introduction

Personal finance is one of the most common sources of stress for young people. Students and young professionals typically receive a limited income - a scholarship, a part-time salary or a first paycheck - and must stretch it across rent, food, transport and leisure. Yet most of them have no clear picture of where their money actually goes. Bank statements are consulted too late, spreadsheets are abandoned after a week, and traditional budgeting applications are often designed for financially literate adults with stable salaries, investments and credit products. The result is a well-documented paradox: young people care about money more than ever, but feel less in control of it than any previous generation.

The Flousy project was born from this observation. Flousy is a mobile application for personal budgeting and savings management, designed specifically for students aged 18 to 25 and young working adults aged 25 to 35. Its promise is simple: allow every young person to understand and control their finances in no more than five minutes per day. The application allows users to record transactions manually or automatically, categorises expenses into intuitive envelopes (rent, food, leisure, transport), triggers alerts when a budget envelope is about to be exceeded, and helps users set and track concrete savings goals such as a trip, a laptop or an emergency fund.

To deliver this product in a controlled and iterative way, the project adopts the Scrum framework. The work is organised into four sprints of two weeks each, covering a total duration of eight weeks. The team is composed of five members: Salma acts as Product Owner and is responsible for the product vision and backlog prioritisation; Youssef acts as Scrum Master and facilitates the ceremonies while removing impediments; Omar is the front-end developer, Nada is the back-end developer, and Reda is the UX/UI designer. This composition allows the team to cover the full delivery chain, from user research and interface design to implementation and testing.

This document constitutes the complete sprint planning report for Week 1 of the project. Its purpose is to define a strategic approach for managing the project in an agile way. It presents the product vision and the SMART objectives derived from it, the eight-week roadmap with its four sprints and key milestones, the prioritised product backlog expressed as user stories following the MoSCoW method, the detailed breakdown of the most critical stories into technical tasks, the day-by-day plan for Sprint 1, a structured analysis of the potential risks together with mitigation and contingency strategies, and finally the expectations of the stakeholders and the way the team intends to address them. The document is intended to serve both as a contractual reference for the team and as a communication tool towards the stakeholders.

# 2. Project Vision and Objectives

## 2.1 Vision Statement

"Help every young person master their finances in 5 minutes a day."

This vision statement guides every prioritisation decision made during the project. It contains three commitments. First, the product targets young people specifically: every design choice, from vocabulary to colour palette, must be accessible to users with no financial background. Second, the product aims at mastery, not just tracking: Flousy must change behaviour, not only display numbers. Third, the product must fit into five minutes of daily use: any feature that requires more effort than this is, by definition, out of scope for the first version.

## 2.2 SMART Objectives

The vision is translated into five SMART objectives (Specific, Measurable, Achievable, Realistic, Time-bound) that will be used to evaluate the success of the project at the end of the eight weeks:

- Objective 1 - Functional core: deliver, by the end of Sprint 4 (27 February 2026), a working mobile prototype covering the four core features: transaction entry (manual and simulated automatic import), expense categorisation, budget overrun alerts and savings goals.

- Objective 2 - Quality: reach a test coverage of at least 70% on the back-end business logic and zero critical bugs open at the final Sprint Review.

- Objective 3 - Usability: obtain a System Usability Scale (SUS) score of at least 75 out of 100 during the user testing session organised in Sprint 4 with a panel of 10 target users.

- Objective 4 - Adoption simulation: have at least 80% of the test panel declare that they would use the application daily, measured through the end-of-test questionnaire.

- Objective 5 - Process: maintain a sprint velocity within +/- 20% of the planned capacity across the four sprints, demonstrating the team's ability to estimate and deliver reliably.

## 2.3 Project Scope

### Included in scope

- Manual entry of income and expenses (amount, category, date, optional note).

- Simulated automatic import of transactions from a CSV bank statement file.

- Automatic categorisation into four default envelopes: rent, food, leisure and transport.

- Monthly budget definition per envelope and visual overrun alerts.

- Creation and tracking of savings goals with progress indicators.

- Dashboard summarising the monthly situation in a single screen.

### Excluded from scope (out of scope for V1)

- Real connection to banking APIs (aggregation): simulated through CSV import only.

- Multi-currency management, cryptocurrency or investment tracking.

- Social features (shared budgets, group expenses, challenges between friends).

- Native iOS publication: the prototype targets Android first, with a responsive web fallback.

- Monetisation features (premium subscriptions, advertising).

## 2.4 Added Value for Users

For the target audience, the added value of Flousy is threefold. Financially, the application transforms an opaque bank balance into an intelligible daily picture: the user knows at any moment how much remains in each envelope and can therefore make informed spending decisions. Psychologically, the savings goals and progress bars introduce positive reinforcement: instead of feeling guilty about spending, the user is rewarded for saving, which is the mechanism most likely to create a durable habit. Practically, the five-minute daily ritual - open the app, check the dashboard, confirm the day's transactions - is deliberately smaller than any competing routine, which lowers the barrier to adoption for an audience that abandons tools quickly. For the stakeholders, the project is also a pedagogical vehicle: it demonstrates the complete Scrum lifecycle on a realistic product, from vision to potentially shippable increment.

# 3. Project Roadmap

The project is divided into four sprints of two weeks, from Monday 5 January 2026 to Friday 27 February 2026. Each sprint delivers a potentially shippable increment and ends with a Sprint Review in front of the stakeholders, followed by a Sprint Retrospective. The global logic is progressive: Sprint 1 lays the technical and functional foundations, Sprint 2 builds the budgeting intelligence, Sprint 3 delivers the savings dimension and the automatic import, and Sprint 4 is dedicated to consolidation, user testing and release preparation.

| Sprint | Dates (2026) | Sprint goal | Main user stories | Key deliverables |
| --- | --- | --- | --- | --- |
| Sprint 1 | 5 Jan - 16 Jan | Set up the foundations and deliver basic manual transaction entry | US-01, US-02, US-03 | Technical environment, app skeleton, manual transaction entry, category list |
| Sprint 2 | 19 Jan - 30 Jan | Deliver the budgeting engine: envelopes and overrun alerts | US-04, US-05, US-06 | Monthly budget per envelope, dashboard v1, push/in-app alerts |
| Sprint 3 | 2 Feb - 13 Feb | Deliver savings goals and automatic CSV import | US-07, US-08, US-09 | Savings goals with progress, CSV import, transaction history and search |
| Sprint 4 | 16 Feb - 27 Feb | Consolidate, test with users and release V1 | US-10, US-11, US-12 | Onboarding, user test report, bug fixing, V1 release candidate |

Table 1 - Roadmap of the four sprints

## 3.1 Key Milestones

- M1 - Friday 9 January 2026: environment ready, CI pipeline green, product backlog validated by the Product Owner.

- M2 - Friday 16 January 2026: end of Sprint 1 - a user can record and view a manual transaction end to end.

- M3 - Friday 30 January 2026: end of Sprint 2 - the budgeting loop (budget definition, dashboard, alert) is functional.

- M4 - Friday 13 February 2026: end of Sprint 3 - feature complete: all Must and Should stories delivered.

- M5 - Wednesday 25 February 2026: user testing session with the panel of 10 target users.

- M6 - Friday 27 February 2026: final Sprint Review and delivery of the V1 release candidate.

## 3.2 Textual Diagram of the Roadmap

Jan                Feb

Wk  1   2   3   4   5   6   7   8

|===Sprint 1===|===Sprint 2===|===Sprint 3===|===Sprint 4===|

Foundations    Budget engine   Savings +     Tests + release

+ manual entry + alerts        CSV import    candidate

M1  M2         M3              M4          M5    M6

Figure 1 - Eight-week roadmap of the Flousy project

# 4. Product Backlog and User Stories

## 4.1 Prioritisation Method: MoSCoW

The product backlog is prioritised using the MoSCoW method, which classifies each requirement into four categories. Must have stories are non-negotiable: without them, the product has no reason to exist and the sprint or release is considered a failure. Should have stories are important but not vital; the product remains usable without them, although noticeably less attractive. Could have stories are desirable improvements that will be implemented only if capacity allows. Won't have stories are explicitly excluded from the current version: listing them prevents scope creep by making the exclusion visible and agreed. Combined with Fibonacci estimation (1, 2, 3, 5, 8, 13 story points), this method gives the Product Owner a transparent trade-off mechanism: when new ideas emerge during the project, they can only enter a sprint if an item of equivalent size leaves it.

## 4.2 Product Backlog

| ID | User story (As a... I want... so that...) | Priority (MoSCoW) | Estimation (points) | Target sprint |
| --- | --- | --- | --- | --- |
| US-01 | As a student, I want to manually add an expense or income (amount, category, date) so that I can keep track of my money day by day. | Must | 5 | Sprint 1 |
| US-02 | As a user, I want to see the list of my transactions sorted by date so that I can review my recent activity. | Must | 3 | Sprint 1 |
| US-03 | As a user, I want the expenses to be classified into categories (rent, food, leisure, transport) so that I understand where my money goes. | Must | 5 | Sprint 1 |
| US-04 | As a young professional, I want to define a monthly budget for each category so that I control my spending limits. | Must | 5 | Sprint 2 |
| US-05 | As a user, I want to receive an alert when I approach or exceed a category budget so that I can react before it is too late. | Must | 8 | Sprint 2 |
| US-06 | As a user, I want a dashboard summarising my month (balance, spending by category, remaining budgets) so that I grasp my situation in one glance. | Must | 8 | Sprint 2 |
| US-07 | As a student, I want to create a savings goal (name, target amount, deadline) so that I stay motivated to put money aside. | Must | 5 | Sprint 3 |
| US-08 | As a user, I want to see the progress of my savings goals as a percentage bar so that I feel encouraged to continue. | Should | 3 | Sprint 3 |
| US-09 | As a user, I want to import a CSV bank statement so that my transactions are added automatically without manual entry. | Should | 8 | Sprint 3 |
| US-10 | As a new user, I want a short onboarding tutorial so that I understand the app in less than two minutes. | Should | 3 | Sprint 4 |
| US-11 | As a user, I want to edit or delete a transaction so that I can correct mistakes. | Should | 3 | Sprint 4 |
| US-12 | As a user, I want a dark mode so that the app is comfortable to use at night. | Could | 2 | Sprint 4 |
| US-13 | As a user, I want to share a budget with my flatmates so that we manage common expenses together. | Won't (V1) | 13 | Backlog |
| US-14 | As a user, I want a direct connection to my bank API so that transactions sync in real time. | Won't (V1) | 13 | Backlog |

Table 2 - Prioritised product backlog (14 user stories, 61 points in scope for V1)

The total scope of version 1 (Must + Should + Could) represents 61 story points. With an estimated team velocity of 13 to 16 points per sprint, this scope is ambitious but achievable, and the Could items act as a buffer: they will only be pulled into a sprint if the Must and Should items are completed ahead of schedule.

## 4.3 Acceptance Criteria of the Three Most Important Stories

### US-01 - Manual transaction entry (Must, 5 points)

- Given the user is on the dashboard, when they tap the "+" button, then the transaction form opens in less than one second.

- Given the form is open, when the user enters an amount, selects a category and a date and confirms, then the transaction is saved locally and appears at the top of the transaction list.

- Given the user leaves the amount field empty or enters a negative value, when they try to confirm, then a clear error message is displayed and nothing is saved.

- Given a transaction was just saved, when the user closes and reopens the application, then the transaction is still present (persistence).

### US-05 - Budget overrun alert (Must, 8 points)

- Given a monthly budget is defined for a category, when the cumulative expenses of that category reach 80% of the budget, then a warning alert (orange) is displayed on the dashboard.

- Given the cumulative expenses exceed 100% of the budget, when the user opens the app or adds a new expense, then a critical alert (red) is triggered with the exceeded amount.

- Given an alert was triggered, when the user dismisses it, then it does not reappear for the same threshold during the same day.

- Given no budget is defined for a category, when expenses are recorded in that category, then no alert is triggered and no error occurs.

### US-07 - Savings goal creation (Must, 5 points)

- Given the user is on the savings screen, when they create a goal with a name, a target amount and a deadline, then the goal is saved and displayed with a progress bar at 0%.

- Given a goal exists, when the user allocates an amount to it, then the progress bar and percentage are updated immediately.

- Given the allocated total reaches the target amount, when the progress reaches 100%, then a congratulation message is displayed and the goal is marked as achieved.

# 5. Task Breakdown

User stories are planning units, but the team works on tasks. During Sprint Planning, each selected story is decomposed into technical tasks of less than one day of work, each assigned to a team member with an hourly estimate. This section details the decomposition of the three stories selected for Sprint 1: US-01 (manual transaction entry), US-02 (transaction list) and US-03 (categorisation).

## 5.1 US-01 - Manual Transaction Entry (total: 24 hours)

| Task ID | Technical sub-task | Responsible | Duration (hours) | Status |
| --- | --- | --- | --- | --- |
| T-01.1 | Design the transaction form mock-up (fields, validation states) | Reda (UX/UI) | 4 | To do |
| T-01.2 | Create the Transaction data model and local database schema | Nada (Back-end) | 4 | To do |
| T-01.3 | Implement the entry form screen with field validation | Omar (Front-end) | 8 | To do |
| T-01.4 | Implement the save/persistence layer and error handling | Nada (Back-end) | 4 | To do |
| T-01.5 | Unit tests on validation rules + integration test of the save flow | Omar + Nada | 4 | To do |

Table 3 - Task breakdown of US-01 - 24 hours

## 5.2 US-02 - Transaction List (total: 12 hours)

| Task ID | Technical sub-task | Responsible | Duration (hours) | Status |
| --- | --- | --- | --- | --- |
| T-02.1 | Design the transaction list screen (cards, date grouping) | Reda (UX/UI) | 3 | To do |
| T-02.2 | Implement the list screen with date-sorted rendering | Omar (Front-end) | 5 | To do |
| T-02.3 | Implement the read query (ordered retrieval, pagination) | Nada (Back-end) | 2 | To do |
| T-02.4 | Test the list with 200+ transactions (performance check) | Omar (Front-end) | 2 | To do |

Table 4 - Task breakdown of US-02 - 12 hours

## 5.3 US-03 - Expense Categorisation (total: 16 hours)

| Task ID | Technical sub-task | Responsible | Duration (hours) | Status |
| --- | --- | --- | --- | --- |
| T-03.1 | Define the category model (4 default envelopes, icons, colours) | Reda + Salma | 3 | To do |
| T-03.2 | Implement the category selector component in the entry form | Omar (Front-end) | 5 | To do |
| T-03.3 | Implement category aggregation queries (totals per envelope) | Nada (Back-end) | 4 | To do |
| T-03.4 | Display per-category totals on a first summary view | Omar (Front-end) | 4 | To do |

Table 5 - Task breakdown of US-03 - 16 hours

The three stories represent a total of 52 hours of estimated work. With four production members (Reda, Omar, Nada, and Salma contributing part-time on product topics) available approximately 6 hours per day over 10 working days, the theoretical capacity of the sprint is around 240 hours. The 52 hours of story tasks, plus roughly 30 hours of environment setup, ceremonies and code review, leave a comfortable margin that the team deliberately keeps for unforeseen technical difficulties - a direct application of the agile principle of sustainable pace.

# 6. Sprint 1 Planning

## 6.1 Sprint Goal

"By the end of Sprint 1, a user can install the application skeleton, manually record an expense or income with its category, and see it appear in a date-sorted list with per-category totals - proving that the technical foundations and the core data flow work end to end."

## 6.2 Sprint Backlog

| ID | User story | Priority | Story points |
| --- | --- | --- | --- |
| US-01 | Manual transaction entry (amount, category, date) | Must | 5 |
| US-02 | Transaction list sorted by date | Must | 3 |
| US-03 | Expense categorisation into the four default envelopes | Must | 5 |
|  | TOTAL |  | 13 |

Table 6 - Sprint 1 backlog

## 6.3 Team Capacity

The capacity is calculated as follows. The sprint contains 10 working days. Four members contribute to production: Omar and Nada at 100% (6 productive hours per day each), Reda at 100% on design tasks, and Salma at 50% (her other half being dedicated to Product Owner duties: backlog refinement and stakeholder communication). Youssef, as Scrum Master, does not take development tasks but reserves time for facilitation and impediment removal. This gives a theoretical capacity of about 210 to 240 hours. In story points, the team - which has no velocity history - conservatively commits to 13 points, the three Must stories of Sprint 1, which corresponds to 52 estimated task hours plus setup and ceremonies. Committing below theoretical capacity for the first sprint is a deliberate choice: it protects the Sprint Goal against the unknowns of a new team and a new technical stack.

## 6.4 Day-by-Day Timeline (5 - 16 January 2026)

| Day | Date (2026) | Planned activities |
| --- | --- | --- |
| J1 | Mon 5 Jan | Sprint Planning (whole team, 4h): validate the Sprint Goal, decompose stories into tasks. Environment setup begins (Git repository, project skeleton). |
| J2 | Tue 6 Jan | Environment setup: CI pipeline, code review rules, local database. Reda starts the mock-ups (T-01.1). |
| J3 | Wed 7 Jan | Nada implements the data model (T-01.2). Reda delivers the form mock-up. Daily Stand-up #1 in the morning. |
| J4 | Thu 8 Jan | Omar starts the entry form (T-01.3). Nada starts the persistence layer (T-01.4). |
| J5 | Fri 9 Jan | MILESTONE M1: environment ready, CI green. Mid-sprint informal checkpoint: mock-ups validated by Salma. |
| J6 | Mon 12 Jan | Omar continues the form; Nada finishes persistence. Reda designs the list screen (T-02.1). |
| J7 | Tue 13 Jan | Category selector component (T-03.2). First end-to-end test: save a transaction and read it back. |
| J8 | Wed 14 Jan | Transaction list implementation (T-02.2) and read query (T-02.3). |
| J9 | Thu 15 Jan | Category totals view (T-03.4). Unit and integration tests (T-01.5, T-02.4). Bug fixing. |
| J10 | Fri 16 Jan | MILESTONE M2: Sprint Review (demo to stakeholders, 2h) then Sprint Retrospective (1h30). Sprint 1 officially closed. |

Table 7 - Day-by-day plan of Sprint 1

## 6.5 Scrum Ceremonies During the Sprint

- Daily Stand-up (15 min, every morning at 9:30): each member answers the three questions - what did I do yesterday, what will I do today, what is blocking me. Impediments are noted by Youssef and treated after the meeting.

- Sprint Planning (J1, 4 hours): definition of the Sprint Goal, selection of the stories, decomposition into tasks and hourly estimates.

- Sprint Review (J10, 2 hours): live demonstration of the increment to the stakeholders, collection of feedback, update of the product backlog by Salma.

- Sprint Retrospective (J10, 1h30): the team inspects its own collaboration using the Start / Stop / Continue format and selects one concrete improvement action for Sprint 2.

- Backlog Refinement (mid-sprint, 1 hour): Salma and the team clarify the stories of Sprint 2 (US-04 to US-06) so that the next Sprint Planning takes less than two hours.

# 7. Risk Analysis

Risk management in an agile project is continuous rather than periodic: risks are identified at planning time, reviewed implicitly at each Daily Stand-up, and formally reassessed at each Sprint Retrospective. Each risk below is scored on probability (Low = 1, Medium = 2, High = 3) and impact (Low = 1, Medium = 2, High = 3, Very high = 4). The criticality score is the product of the two values; risks scoring 6 or more receive a named owner and a contingency plan in addition to their mitigation strategy.

| ID | Description | Category | Probability | Impact | Score | Mitigation strategy | Contingency plan | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-01 | Team members unavailable (exams, part-time jobs) during the sprint | Human | High | High | 9 | Plan capacity at 60-70%; cross-train members on each other's tasks | Descope the Could/Should stories of the sprint; renegotiate the Sprint Goal with the PO | Youssef |
| R-02 | Learning curve on the mobile framework slows down development | Technical | High | Medium | 6 | Dedicate J2-J3 to technical spikes; pair programming on the first complex screens | Simplify the UI (drop animations, use native components) | Omar |
| R-03 | Scope creep: stakeholders request new features mid-sprint | Project | Medium | High | 6 | PO acts as single entry point; all requests go to the backlog, never directly into the sprint | Formal change request reviewed at the next Sprint Planning only | Salma |
| R-04 | CSV bank statement formats differ between banks, breaking the import (Sprint 3) | Technical | Medium | Medium | 4 | Collect sample files from 3 banks early; design a configurable column-mapping | Restrict V1 import to the 2 most common formats, documented for users | Nada |
| R-05 | Loss of work (no version control discipline, broken laptop) | Technical | Low | Very high | 4 | Mandatory Git with daily pushes; protected main branch; CI on every push | Restore from the last green CI build; maximum one day of work lost | Youssef |
| R-06 | Misunderstood requirements: the increment does not match the PO's expectations | Communication | Medium | High | 6 | Acceptance criteria written for every Must story; PO available daily; mid-sprint checkpoint (J5) | Demonstrate early and often; correct in the following sprint if minor | Salma |
| R-07 | Conflicts or communication breakdown inside the team | Human | Low | High | 3 | Daily Stand-up as a transparency ritual; retrospective as a safe space to raise tensions | Scrum Master mediation; escalation to the supervising professor if unresolved | Youssef |
| R-08 | User test panel (Sprint 4) hard to recruit or unrepresentative | External | Medium | Medium | 4 | Recruit 15 volunteers from the start (5 backups); small incentive (vouchers) | Fallback on remote moderated tests with screen sharing | Salma |
| R-09 | Estimation errors: stories take much longer than planned | Project | Medium | Medium | 4 | Fibonacci relative estimation; tasks capped at 8 hours; re-estimate at mid-sprint | Apply the MoSCoW buffer: drop Could items, protect the Sprint Goal | Whole team |

Table 8 - Risk register of the Flousy project (probability x impact = score, maximum 12)

## 7.1 Explanation of the Mitigation Strategies

Three logics govern the mitigation strategies. The first is prevention at the source: risks R-01, R-05 and R-09 are reduced by working agreements - realistic capacity planning, mandatory version control and relative estimation - that cost little but remove entire classes of problems before they appear. The second is early feedback: risks R-03 and R-06, which concern the adequacy between what is built and what is expected, are mitigated by shortening the feedback loop (written acceptance criteria, mid-sprint checkpoint, Sprint Review), so that a misunderstanding can never survive longer than a few days. The third is controlled degradation: for risks that cannot be fully prevented, such as R-02 and R-04, the mitigation prepares a simplified but still valuable version of the feature, guaranteeing that even in the worst case the sprint delivers something demonstrable.

## 7.2 Continuous Risk Monitoring

- Daily: the Stand-up explicitly asks "what is blocking me?", which surfaces emerging risks within 24 hours.

- Weekly: Youssef reviews the risk register every Friday and updates probabilities and scores.

- Per sprint: the Retrospective includes a standing "risks" item; new risks are added to the register with an owner.

- Escalation rule: any risk whose score reaches 9 or more is reported immediately to the supervising professor and discussed at the next Daily Stand-up.

- Visibility: the risk register is stored in the shared project space and accessible to all stakeholders at any time.

# 8. Stakeholder Expectations

A project succeeds when it satisfies its stakeholders, not only when its code works. The Flousy project involves seven categories of stakeholders, whose expectations, influence and the team's response are summarised below.

| Stakeholder | Main expectation | How the team responds | Influence level |
| --- | --- | --- | --- |
| End users (students, young professionals) | A simple, fast, non-judgmental app that really helps them save | User-centred design led by Reda; SUS usability test in Sprint 4 with a panel of 10 target users | High (via feedback) |
| Product Owner (Salma) | A backlog that reflects the vision; maximised product value each sprint | Owns the backlog; validates acceptance criteria; arbitrates priorities at each Sprint Planning | Very high |
| Scrum Master (Youssef) | A respected process and a protected, self-organised team | Facilitates ceremonies, removes impediments, monitors the risk register weekly | High |
| Development team (Omar, Nada, Reda) | Clear requirements, realistic workload, technical quality | Tasks capped at 8h; acceptance criteria per story; Definition of Done enforced | High |
| Supervising professor | Rigorous application of Scrum and a professional deliverable | This planning document; Sprint Reviews open to the professor; traceable artefacts | Very high |
| Future partner banks | Data handling that respects privacy and banking constraints | V1 uses CSV import only (no API); privacy noted as a constraint for V2 | Medium |
| University / academic institution | A pedagogically sound project demonstrating agile mastery | Documented ceremonies, artefacts and metrics (velocity, burndown) | Medium |

Table 9 - Stakeholder expectations and team responses

## 8.1 Power / Interest Matrix

High power  |  KEEP SATISFIED          |  MANAGE CLOSELY

|  - Partner banks          |  - Supervising professor

|  - University             |  - Product Owner (Salma)

|                           |  - Scrum Master (Youssef)

-----------+-----------------------------------------------

Low power   |  MONITOR                  |  KEEP INFORMED

|  - Media / general public |  - End users (test panel)

|                           |  - Dev team members

+-----------------------------------------------

Low interest              High interest

Figure 2 - Power/Interest matrix of the Flousy project

## 8.2 Communication Strategy

| Audience | Content | Frequency / moment | Channel |
| --- | --- | --- | --- |
| Whole team | Progress, impediments, plan of the day | Daily (9:30, 15 min) | Stand-up meeting |
| Product Owner + team | Backlog clarification, upcoming stories | Mid-sprint (1h) | Refinement workshop |
| Stakeholders + professor | Demonstration of the increment, feedback | End of each sprint | Sprint Review (video call) |
| Professor | Written status: velocity, burndown, risks | Every two weeks | Short email report |
| End users (panel) | Test invitations, results summary | Sprint 4 | Messaging group + survey |

Table 10 - Communication plan

# 9. Conclusion

This planning document provides the Flousy project with a complete and coherent framework for its eight weeks of execution. Starting from a clear vision - helping every young person master their finances in five minutes a day - it derives five SMART objectives, a four-sprint roadmap with dated milestones, a prioritised backlog of fourteen user stories estimated in Fibonacci points, and a detailed task-level plan for Sprint 1, whose goal is to prove the end-to-end data flow with manual transaction entry, listing and categorisation. The risk analysis identifies nine risks, three of them critical enough to carry both a mitigation strategy and a contingency plan with a named owner, and embeds risk surveillance into the daily and sprint-level rituals. Finally, the stakeholder analysis maps expectations, influence and the communication channels that will keep every party aligned.

The immediate next steps are the Sprint Planning session of Monday 5 January, the environment setup of the first two days, and the mid-sprint checkpoint of Friday 9 January. Three factors will be decisive for success: the discipline of the team in respecting the ceremonies and the Definition of Done, the availability and reactivity of the Product Owner in arbitrating priorities, and the team's ability to protect the Sprint Goal by descoping secondary items rather than sacrificing quality. With these conditions met, the project is positioned to deliver, on 27 February 2026, a version 1 that is small but complete, tested with real users, and faithful to its vision.

# 10. Appendices

## Appendix A - Burndown Chart Model (Sprint 1)

The burndown chart tracks the remaining work in the sprint, measured in task hours, against the 10 working days. The ideal line descends linearly from 52 hours (J1) to 0 (J10). Each morning, after the Stand-up, the Scrum Master plots the actual remaining hours; a gap above the ideal line for two consecutive days triggers a discussion on scope or impediments.

Hours

52 |*

45 | * *

39 |    *  <- actual

32 |      *

26 |        *

19 |          *

13 |            *

6 |              *

0 |________________*____

J1 J2 J3 J4 J5 J6 J7 J8 J9 J10

- - - - ideal line / * actual remaining hours

## Appendix B - Daily Stand-up Template

- Time: every working day, 9:30 - 9:45 (15 minutes, standing).

- Round table - each member answers: (1) What did I complete yesterday? (2) What will I do today? (3) Is anything blocking me?

- The Scrum Master records impediments on the impediment board and assigns an owner and a deadline to each.

- No problem-solving during the Stand-up: technical discussions continue afterwards between the concerned members only.

## Appendix C - Definition of Done (DoD)

A user story is "Done" only when ALL the following conditions are met:

- All tasks of the story are completed and the acceptance criteria are verified one by one.

- The code is pushed to the main branch, reviewed by at least one other member, and the CI pipeline is green.

- Unit tests cover the new business logic; no critical or major bug remains open.

- The feature works on the reference device without regression on existing features.

- The Product Owner has seen the feature running and explicitly accepted it.

- User-facing text is proofread; any new screen follows the design system defined in Sprint 1.