FLOUSY

Agile Execution Plan - Flousy Project

Agile Execution and Team Coordination - Week 2

Student name: Meryem Zagui

Subject: Agile Project Management

Project: Flousy - personal budgeting mobile app

Period: January 5 - February 27, 2026 (4 Sprints)

Table of Contents

1. Introduction	1

2. Principles of Agile Execution	1

2.1 Scrum Ceremonies	1

2.2 Artifacts	1

2.3 Agile Values Applied to Execution	1

2.4 The Scrum Master's Role in Execution	1

3. Team Organization and Task Delegation	1

3.1 Team Presentation	1

3.2 Task Delegation Method	1

3.3 RACI Matrix for Key Sprint 1 Tasks	1

3.4 Detailed Sprint 1 Delegation Table	1

3.5 Accountability Rules	1

3.6 Concrete Example	1

4. Team Communication	1

4.1 Channels and Usage Rules	1

4.2 Communication Flow Chart	1

4.3 Template Message to Report a Blocker	1

4.4 Meeting Rules	1

4.5 Communication Matrix	1

5. Daily Stand-up Meetings	1

5.1 Purpose and Rules	1

5.2 The Three Questions	1

5.3 Daily Template	1

5.4 Impediment Management	1

5.5 Example Run-through for Flousy (Day 4 - Thursday, January 8)	1

5.6 Best Practices and Mistakes to Avoid	1

6. Sprint Tracking Tools	1

6.1 Burndown Chart	1

6.2 Kanban Board	1

6.3 Velocity Chart	1

6.4 Story Points and Team Capacity	1

6.5 Digital Tools	1

6.6 Tracking Dashboard	1

7. Issue Escalation Process	1

7.1 Definition of an Escalatable Issue	1

7.2 Escalation Levels	1

7.3 Flow Diagram	1

7.4 Time Limits and Transition Rules	1

7.5 Escalation Ticket Template	1

7.6 Concrete Examples for Flousy	1

8. Adaptive Planning and Resource Allocation	1

8.1 Principle of Adaptation	1

8.2 Handling Unforeseen Events	1

8.3 Resource Reallocation	1

8.4 Descoping	1

8.5 Concrete Example: Reallocating Nada to One of Omar's Tasks	1

8.6 Role of the PO and the SM	1

9. Practical Application to Flousy's Sprint 1	1

9.1 Sprint Goal	1

9.2 Application of the Tools	1

9.3 Typical Day	1

9.4 Sprint 1 Kanban Board (status on Day 5 - Friday, January 9)	1

9.5 Expected Results at the End of Sprint 1	1

10. Conclusion	1

Appendices	1

Appendix A: Daily Stand-up Template	1

Appendix B: Escalation Ticket Template	1

Appendix C: Sprint 1 Burndown Chart	1

Appendix D: Communication Flow Chart	1

Appendix E: Complete Sprint 1 RACI Matrix	1

Note: in Word, right-click the table and choose "Update Field" if page numbers do not appear.

# 1. Introduction

Flousy is a personal budgeting and savings mobile application aimed at young adults. Its vision fits in a single sentence: "Help every young person master their finances in 5 minutes a day." The product must therefore be simple, fast to use and motivating enough to become part of the daily routine of an audience that has neither the time nor, often, the financial background to use complex tools.

The Week 1 report laid the foundations of the project: product vision, functional scope, team composition and a breakdown into four two-week Sprints, from January 5 to February 27, 2026. The team has five members: Salma (Product Owner), Youssef (Scrum Master), Omar (Front-end developer), Nada (Back-end developer) and Reda (UX/UI designer). The Sprint goals are: foundations and manual transaction entry (Sprint 1), budget engine and alerts (Sprint 2), savings and CSV import (Sprint 3), then user testing and release (Sprint 4).

Once the framework is in place, the central question becomes: how do we execute this plan day after day? An excellent backlog guarantees nothing if tasks are poorly distributed, if information flows badly or if problems are discovered too late. This report, devoted to the execution phase, aims to build a detailed plan showing how agile methodologies enable effective task management and smooth team coordination. It illustrates delegation strategies, daily meetings, burndown charts, escalation processes and the role of adaptive planning in an evolving project environment.

The document is structured as follows: Section 2 recalls the principles of agile execution; Section 3 presents team organization and task delegation; Section 4 describes team communication; Section 5 details the Daily Stand-ups; Section 6 presents Sprint tracking tools; Section 7 formalizes the escalation process; Section 8 covers adaptive planning and resource allocation; Section 9 applies everything to Flousy's Sprint 1. A conclusion and five appendices (ready-to-use templates) complete the report.

# 2. Principles of Agile Execution

## 2.1 Scrum Ceremonies

Scrum structures execution around time-boxed events that create a predictable rhythm. For Flousy, each two-week Sprint follows the same cycle.

| Ceremony | Purpose | Duration | Timing (Flousy) |
| --- | --- | --- | --- |
| Sprint Planning | Define the Sprint Goal and select Product Backlog items | 2 h | Day 1, 9:30 |
| Daily Stand-up | Synchronize the team, detect blockers | 15 min | Every day, 9:30 |
| Backlog Refinement | Clarify, estimate and order upcoming stories | 1 h | Wednesday of week 2 |
| Sprint Review | Present the Increment and collect feedback | 1 h | Last day, 2:00 pm |
| Retrospective | Improve how the team works | 45 min | Last day, 3:30 pm |

## 2.2 Artifacts

- Product Backlog: ordered list of everything the product needs, owned by Salma.

- Sprint Backlog: stories selected for the Sprint and the plan to deliver them, managed by the developers.

- Increment: usable version of the product meeting the Definition of Done at the end of the Sprint.

- Burndown Chart: curve of remaining work (in Story Points) day by day, detailed in Section 6.

## 2.3 Agile Values Applied to Execution

Three values guide the team's daily work. Collaboration translates into cross-reviews, pair programming and constant dialogue between Salma and the team. Self-organization means developers decide for themselves how to do the work: nobody assigns tasks from the outside. Continuous adaptation relies on frequent inspection (Daily, Review, Retrospective) and the ability to adjust the plan without waiting for the end of the Sprint.

## 2.4 The Scrum Master's Role in Execution

Youssef is not a project manager: he is a servant leader for the team. During execution, he facilitates ceremonies, shields the team from outside interruptions, removes impediments, ensures Scrum rules are followed and maintains the tracking tools (burndown, impediment register). He also coaches Salma on backlog management and helps the team improve using the outcomes of each retrospective.

# 3. Team Organization and Task Delegation

## 3.1 Team Presentation

| Member | Role | Main responsibilities | Key skills |
| --- | --- | --- | --- |
| Salma | Product Owner | Product vision, backlog prioritization, acceptance criteria, story validation | Needs analysis, communication |
| Youssef | Scrum Master | Facilitation, burndown tracking, impediment management, level 2 escalation | Coaching, mediation |
| Omar | Front-end Developer | React Native mobile interface, mockup integration, API calls | React Native, JavaScript |
| Nada | Back-end Developer | API, database, authentication, data security | Node.js, SQL, testing |
| Reda | UX/UI Designer | Mockups, design system, usability testing, accessibility | Figma, user research |

## 3.2 Task Delegation Method

In Scrum, tasks are not imposed: they are chosen by the developers during Sprint Planning, guided by three allocation criteria.

- Skills: the task goes first to the most qualified person, for example the authentication API to Nada.

- Workload: we check that nobody exceeds their capacity (see Section 6.4); no member should carry more than 40% of the Sprint's Story Points.

- Learning: one task in five is deliberately given to a less experienced backup, to build versatility and reduce dependence on a single person.

## 3.3 RACI Matrix for Key Sprint 1 Tasks

The RACI matrix clarifies who is Responsible (does the work), Approver (validates), Consulted (gives input) and Informed. It is adapted here to Scrum: Salma approves stories, the team delivers. The complete matrix is in Appendix E.

| Task | Salma (PO) | Youssef (SM) | Omar | Nada | Reda |
| --- | --- | --- | --- | --- | --- |
| T03 Design system | A | I | C | I | R |
| T06 Authentication API | A | I | C | R | I |
| T08 Transactions API | A | I | C | R | I |
| T09 Entry screen | A | I | R | C | C |
| T11 Sprint acceptance testing | A | R | C | C | C |

## 3.4 Detailed Sprint 1 Delegation Table

The table below presents the initial Sprint Backlog of 40 Story Points (SP). Each task has a single owner and a backup able to take over in case of an unforeseen event.

| ID | Task | SP | Owner | Backup | Deadline | Status |
| --- | --- | --- | --- | --- | --- | --- |
| T01 | GitHub repository + continuous integration | 3 | Nada | Omar | Jan 6 | To do |
| T02 | React Native project + navigation | 3 | Omar | Nada | Jan 7 | To do |
| T03 | Design system and UI guidelines | 5 | Reda | Omar | Jan 9 | To do |
| T04 | Transaction entry mockups | 3 | Reda | Omar | Jan 9 | To do |
| T05 | Database schema | 3 | Nada | Omar | Jan 8 | To do |
| T06 | Sign-up / login API | 5 | Nada | Omar | Jan 12 | To do |
| T07 | Login / sign-up screens | 3 | Omar | Reda | Jan 13 | To do |
| T08 | Transactions CRUD API | 5 | Nada | Omar | Jan 13 | To do |
| T09 | Manual entry screen | 5 | Omar | Nada | Jan 15 | To do |
| T10 | Transaction list + categories | 3 | Omar | Reda | Jan 15 | To do |
| T11 | Testing and Sprint 1 acceptance | 2 | Nada | Omar | Jan 16 | To do |

## 3.5 Accountability Rules

- One single owner per task: shared responsibility is diluted responsibility.

- Mandatory cross-review: no Pull Request is merged without approval from at least one other member.

- Definition of Done (DoD): a task is "Done" when the code is reviewed, unit tests pass (coverage ≥ 70% on business logic), the branch is merged into develop, no critical bug is open, documentation is up to date and Salma has validated the acceptance criteria.

## 3.6 Concrete Example

During the January 5 Sprint Planning, Salma presents the goal "foundations + manual entry". Nada commits to the back-end tasks (T01, T05, T06, T08, T11), i.e. 18 SP, Omar to the front-end (T02, T07, T09, T10), i.e. 14 SP, and Reda to design (T03, T04), i.e. 8 SP. The split is balanced and each backup is identified: if Nada is unavailable, Omar can take over the API thanks to the pair programming planned at the start of the Sprint.

# 4. Team Communication

## 4.1 Channels and Usage Rules

A five-person team can quickly be overwhelmed by notifications if each tool does not have a precise role. Each channel is therefore tied to a purpose, a frequency and clear rules.

| Channel | Purpose | Frequency | Rules |
| --- | --- | --- | --- |
| Slack / Discord | Quick exchanges, blocker alerts, information sharing | Continuous (9-18h) | Channels #general, #dev, #design, #blockers; reply within 2 h; no important decision without a written trace |
| GitHub | Code, Pull Requests, reviews, continuous integration | Daily | One branch per task; PR reviewed within 24 h; explicit commit messages |
| Trello / Jira | Kanban board, backlog, task tracking | Updated before each Daily | Each card = ID, owner, estimate; moved by its owner |
| Email | Formal communication (professor, stakeholders) | Weekly | Standard subject line [Flousy]; minutes sent within 24 h |

## 4.2 Communication Flow Chart

The diagram below illustrates information flows: priority decisions come down from the Product Owner, alerts go up through the Scrum Master, and the team synchronizes every morning.

+--------------------------------------+

|        SUPERVISING PROFESSOR         |

|  Stakeholders (Level 4 escalation)   |

+--------------------------------------+

|

|  Sprint Review / final decisions

v

+----------------------------+                  +----------------------------+

|   Salma - Product Owner    |<--- priorities --->|   Youssef - Scrum Master   |

|Vision, priorities, backlog |<--- arbitration --->| Facilitation, impediments  |

+----------------------------+                  +----------------------------+

|                                               |

|                                               |

v                                               v

+----------------------------------------------------------------------------+

|                     DEVELOPMENT TEAM (self-organizing)                     |

|           Omar (Front-end)  -  Nada (Back-end)  -  Reda (UX/UI)            |

+----------------------------------------------------------------------------+

|

|  Daily Stand-up 9:30 + Kanban + Slack

v

+----------------------------------------------------------------------------+

| CHANNELS: Slack (daily) | GitHub (code) | Trello (tasks) | Email (formal)  |

+----------------------------------------------------------------------------+

Figure 1 - Flousy team communication flow chart

## 4.3 Template Message to Report a Blocker

A poorly reported blocker wastes time. The template below, to be posted in #blockers, fits in six lines and lets Youssef react immediately.

[BLOCKER] T08 - Transactions CRUD API

Who: Nada             Date: 01/12/2026 - 11:15

Problem: database migration fails (foreign key error).

Already tried: rollback, schema check, documentation lookup.

Impact: blocks T09 (Omar) if not solved before tomorrow 5 pm.

Help requested: schema review with Omar (15 min) - Level: 1

## 4.4 Meeting Rules

- Punctuality: start at the exact time; a delay of more than 5 minutes is reported on Slack.

- Agenda: sent at least 24 h before any meeting other than the Daily, with duration and objective.

- Minutes: written by a rotating member, published within 24 h with decisions, actions, owners and deadlines.

- Time-box compliance: any long technical discussion is moved to an "after-Daily" reserved for the people concerned.

## 4.5 Communication Matrix

| Audience | Content | Frequency | Channel | Owner |
| --- | --- | --- | --- | --- |
| Development team | Progress, blockers, daily priorities | Daily | Daily + Slack | Youssef |
| Product Owner | Sprint status, burndown, risks | Daily | Slack + Trello | Youssef |
| Team + PO | Story clarification | Weekly | Refinement | Salma |
| Supervising professor | Progress report, level 4 escalations | Weekly | Email | Youssef |
| Stakeholders / testers | Increment demo | End of Sprint | Sprint Review | Salma |

# 5. Daily Stand-up Meetings

## 5.1 Purpose and Rules

The Daily Stand-up is a synchronization point of 15 minutes maximum, held standing and at the same time every day (9:30 for Flousy, in person or by video call). Its goal is not reporting to a boss, but collectively planning the day and detecting blockers early. Only the developers speak; Salma and Youssef listen. In-depth discussions are moved to the after-Daily.

## 5.2 The Three Questions

- What did I do yesterday? (what moved toward the Sprint Goal)

- What will I do today? (the commitment for the day)

- What is blocking me? (any obstacle, even minor)

## 5.3 Daily Template

Youssef fills in one sheet per day (full template in Appendix A). It includes the date, attendees, each member's items, remaining Story Points and identified impediments.

## 5.4 Impediment Management

An impediment is anything that prevents the team from moving forward. It follows a three-step cycle: identification (during the Daily or at any time in #blockers), logging in the register with an owner and a date, then daily follow-up until resolution. Youssef is the guarantor.

| ID | Impediment | Reported by | Date | Owner | Status |
| --- | --- | --- | --- | --- | --- |
| IMP-01 | Apple developer account unavailable | Omar | Jan 6 | Youssef | In progress |
| IMP-02 | Database migration failing | Nada | Jan 12 | Nada / Omar | Resolved |

## 5.5 Example Run-through for Flousy (Day 4 - Thursday, January 8)

| Participant | Statement |
| --- | --- |
| Youssef | Opening at 9:30. 31 SP remain, slightly above the ideal line (28 SP). Who starts? |
| Omar | Yesterday: React Native navigation done (T02). Today: starting the login screens. Blocker: waiting for the final mockups. |
| Reda | Yesterday: design system at 80%. Today: finalizing and delivering mockups to Omar before noon. No blocker. |
| Nada | Yesterday: database schema validated (T05). Today: starting the authentication API. Blocker: an integration test is failing. |
| Youssef | I log Nada's blocker. Omar and Nada meet for 15 min after the Daily. I update the burndown. End at 9:44. |

## 5.6 Best Practices and Mistakes to Avoid

| Best practices | Mistakes to avoid |
| --- | --- |
| Focus on the Sprint Goal | Turning the Daily into a status report to a manager |
| Update the Kanban before the meeting | Debating a technical problem at length |
| Speak for the team ("we") rather than for oneself | Arriving late or unprepared |
| Report blockers as soon as they appear | Hiding a blocker for fear of judgment |
| Strictly respect the 15 minutes | Letting the meeting drag on without limit |

# 6. Sprint Tracking Tools

## 6.1 Burndown Chart

The Burndown Chart shows remaining work (in Story Points) over time. To build it, start from the total committed at Sprint Planning (40 SP for Sprint 1), draw an ideal line decreasing linearly to zero (4 SP per day over 10 working days), then plot the actual line each day by subtracting only stories that are fully finished, i.e. compliant with the Definition of Done.

Remaining Story Points

40 |  #     *     *

36 |        o           *

32 |              o           *

28 |                    o           *

24 |                          o           *

20 |                                o           *

16 |                                      o           *

12 |                                            o

8 |                                                  o     *

4 |                                                        o     *

0 |  _     _     _     _     _     _     _     _     _     _     o

+------------------------------------------------------------------

0     1     2     3     4     5     6     7     8     9     10    Days (D0 = Jan 5)

Legend :  o = ideal line (40 SP -> 0)   * = actual line   # = ideal and actual overlap

Figure 2 - Sprint 1 Burndown Chart template (illustrative data)

### Interpretation and Corrective Actions

| Observation | Interpretation | Action |
| --- | --- | --- |
| Actual line above the ideal line | Delay: over-optimistic estimates or blockers | Analyze at the Daily, escalate if the gap exceeds 10%, consider descoping |
| Actual line below the ideal line | Ahead of schedule or over-estimated stories | Offer Salma an additional story |
| Flat line then sudden drop | Stories too big, finished late | Split stories further at the next Refinement |
| Line going back up | Added work (scope creep) | Renegotiate with Salma: any addition implies a removal |

## 6.2 Kanban Board

The Kanban board visualizes the workflow in three columns: To Do, In Progress and Done. To avoid scattering effort, the In Progress column is limited to two cards per person (WIP limit). A card moves to Done only when the Definition of Done is met.

## 6.3 Velocity Chart

Velocity is the number of Story Points completed per Sprint. It is used to forecast the capacity of upcoming Sprints, never to compare people. The table below tracks the four Sprints; actual values will be filled in as execution proceeds.

| Sprint | Period | Committed SP (forecast) | Completed SP (actual) |
| --- | --- | --- | --- |
| Sprint 1 | Jan 5 - 16 | 40 | 36 |
| Sprint 2 | Jan 19 - 30 | 40 | 38 |
| Sprint 3 | Feb 2 - 13 | 42 | 42 |
| Sprint 4 | Feb 16 - 27 | 36 (stabilization) | 34 |

## 6.4 Story Points and Team Capacity

Story Points measure the relative effort of a story (Fibonacci sequence: 1, 2, 3, 5, 8) by combining complexity, volume and uncertainty. Sprint 1 capacity is estimated at 40 SP: three developers, 10 days, a realistic availability of 80% after ceremonies and unforeseen events. As Sprint 1 is the first, this estimate is cautious and will be recalibrated using actual velocity.

## 6.5 Digital Tools

| Tool | Strengths | Limitations | Recommended use |
| --- | --- | --- | --- |
| Trello | Simple, free, visual Kanban | No native burndown | Daily Kanban (selected) |
| Jira | Automatic burndown and velocity | Heavier setup | Large projects |
| GitHub Projects | Linked to code and PRs | Limited reports | Complementary technical tracking |
| ClickUp | Versatile, many views | Long learning curve | All-in-one alternative |

## 6.6 Tracking Dashboard

| Indicator | Target | Alert threshold | Source |
| --- | --- | --- | --- |
| Velocity | 38 - 42 SP | < 32 SP | Trello / Sprint sheet |
| Gap to ideal burndown | ≤ 10% | > 15% | Burndown Chart |
| Open critical bugs | 0 | ≥ 2 | GitHub Issues |
| Test coverage | ≥ 70% | < 60% | Continuous integration |
| Pending Pull Requests | < 24 h | > 48 h | GitHub |
| Open impediments | ≤ 2 | ≥ 4 | Impediment register |

# 7. Issue Escalation Process

## 7.1 Definition of an Escalatable Issue

Not every problem is escalatable: a difficulty the team solves alone within a few hours stays at level 1. We escalate when resolution exceeds the capacity or authority of the current level. Four categories are defined.

- Technical blocker: an obstacle preventing a task from progressing (incompatible library, infrastructure error).

- External dependency: a resource or decision outside the team (developer account, access to a banking API).

- Conflict: disagreement over priority, scope or work allocation.

- Critical delay: a gap threatening the Sprint Goal or the release date.

## 7.2 Escalation Levels

| Level | Contact | Resolution time | Criterion to move to next level |
| --- | --- | --- | --- |
| 1 | The team | 24 h | Not solved after 24 h or Sprint Goal impacted |
| 2 | Scrum Master (Youssef) | 48 h | Not solved after 48 h or scope trade-off needed |
| 3 | Product Owner (Salma) | Decision within 24 h | Sprint Goal or release at risk, or PO-team conflict |
| 4 | Management / Supervising Professor | Decision within 72 h | Final decision, no higher escalation |

## 7.3 Flow Diagram

+----------------------------------------------------------+

|                     PROBLEM DETECTED                     |

|     (blocker, dependency, conflict, critical delay)      |

+----------------------------------------------------------+

|

|  Logged in the impediment register

v

+----------------------------------------------------------+

|                      LEVEL 1 - TEAM                      |

|     Collective resolution / pair programming - 24 h      |

+----------------------------------------------------------+

Solved ?  YES --> close the ticket + inform at next Daily

|

|  NO : 24 h exceeded OR Sprint Goal impacted

v

+----------------------------------------------------------+

|             LEVEL 2 - SCRUM MASTER (Youssef)             |

|    Remove obstacle, mediate, contact externals - 48 h    |

+----------------------------------------------------------+

Solved ?  YES --> close + update the burndown

|

|  NO : 48 h exceeded OR scope trade-off required

v

+----------------------------------------------------------+

|             LEVEL 3 - PRODUCT OWNER (Salma)              |

| Priority arbitration / descoping - decision within 24 h  |

+----------------------------------------------------------+

Solved ?  YES --> backlog updated + team informed

|

|  NO : Sprint Goal or release at risk / PO-team conflict

v

+----------------------------------------------------------+

|       LEVEL 4 - MANAGEMENT / SUPERVISING PROFESSOR       |

|  Final decision and resource arbitration - within 72 h   |

+----------------------------------------------------------+

Decision documented --> shared with the whole team + retrospective

Figure 3 - Escalation process flow

## 7.4 Time Limits and Transition Rules

- The clock starts when the issue is logged in the register, not when it appears.

- Moving to the next level is automatic when the time limit expires: nobody has to justify escalating.

- A problem that immediately threatens the Sprint Goal may skip a level on the Scrum Master's decision.

- Every escalation is documented in a ticket (Appendix B) and its outcome is discussed in the Retrospective.

## 7.5 Escalation Ticket Template

| Field | Content |
| --- | --- |
| Problem | Factual description of the problem |
| Impact | Tasks, Sprint Goal or schedule affected |
| Level | 1 / 2 / 3 / 4 |
| Decision | Solution adopted or arbitration made |
| Owner | Person in charge of applying the decision |
| Date | Date reported, escalated and closed |

## 7.6 Concrete Examples for Flousy

| Situation | Progress | Outcome |
| --- | --- | --- |
| React Native technical blocker: the navigation library is incompatible with the framework version | L1: Omar and Nada test for 24 h without success. L2: Youssef consults documentation and the community, proposes an alternative version. | Solved at level 2 in 36 h |
| Priority conflict: Salma wants to add budget alerts in Sprint 1 | L1: the team explains the impact. L2: Youssef mediates. L3: Salma arbitrates according to the product vision. | Alerts kept in Sprint 2 |
| Delivery delay: the transactions API (T08) is 2 days late and blocks the entry screen | L1: pair programming. L2: Youssef notes a 20% gap. L3: Salma removes T10 from the Sprint. | Sprint Goal protected by descoping |

# 8. Adaptive Planning and Resource Allocation

## 8.1 Principle of Adaptation

An agile plan is not a fixed contract: it is a hypothesis continuously revised. During the Sprint, the Sprint Goal stays fixed while the scope is negotiable. At each Daily, the team compares the burndown to the ideal line and decides whether an adjustment is needed, rather than waiting for the end of the Sprint to notice the gap.

## 8.2 Handling Unforeseen Events

| Event | Immediate response | Decision maker |
| --- | --- | --- |
| Absence of a member | Recalculate capacity, backup takes over | Team + Youssef |
| Critical bug in production or testing | Top priority, added to the Sprint with an equivalent removal | Salma |
| Priority change | Integrated in the next Sprint, unless justified urgency | Salma |
| Wrong estimate | Re-estimation and information at the Daily | Team |

## 8.3 Resource Reallocation

In case of overload, the team applies a simple rule: finish before starting. Available members help on tasks in the In Progress column before starting new ones. Reallocation relies on the backups designated in Section 3.4 and on pair programming, which transfers knowledge along with the work.

## 8.4 Descoping

When capacity becomes insufficient, Salma removes non-critical stories to protect the Sprint Goal, using the MoSCoW method (Must, Should, Could, Won't). For Sprint 1, the Must stories are T01 to T09; T10 (enhanced list) is a Should and T11 is a non-negotiable quality activity. A removed story goes back to the Product Backlog, never to the trash.

## 8.5 Concrete Example: Reallocating Nada to One of Omar's Tasks

On Day 6 (January 12), Omar is absent for two days for personal reasons: 8 SP of capacity disappear and T09 (entry screen, 5 SP) becomes critical. Nada, who finished T08 a day early, offers to take over the logic part of T09 (field validation, API calls), while Reda adjusts the layout. T10 is reclassified as a Should and postponed if necessary. Result: the Sprint Goal is preserved, and front-end code knowledge is shared.

## 8.6 Role of the PO and the SM

- Salma (PO): arbitrates scope, decides on descoping, clarifies acceptance criteria and remains available during the Sprint.

- Youssef (SM): detects gaps through the burndown, facilitates reallocation, shields the team from distractions and triggers escalation when needed.

# 9. Practical Application to Flousy's Sprint 1

## 9.1 Sprint Goal

Sprint 1 Goal: "Set up the technical and graphic foundations of Flousy and allow a user to create an account and manually record their transactions."

## 9.2 Application of the Tools

- Daily Stand-up every day at 9:30, with the burndown updated by Youssef right after.

- Burndown Chart tracked daily; a gap above 10% triggers a discussion at the next Daily.

- Escalation: the impediment register is reviewed at every Daily; the 24 h and 48 h time limits apply.

- Cross-review of every Pull Request before merging into develop.

## 9.3 Typical Day

| Time | Activity |
| --- | --- |
| 9:30 - 9:45 | Daily Stand-up |
| 9:45 - 12:30 | Focused development, pair programming if needed |
| 12:30 - 1:30 pm | Lunch break |
| 1:30 - 3:30 pm | Development and integration |
| 3:30 - 4:00 pm | Cross-review of Pull Requests |
| 4:00 - 5:30 pm | Testing, fixes and documentation |
| 5:30 - 6:00 pm | Update Kanban, burndown and impediment register |

## 9.4 Sprint 1 Kanban Board (status on Day 5 - Friday, January 9)

| To Do | In Progress | Done |
| --- | --- | --- |
| T06 Authentication API (5) T07 Login screens (3) T08 Transactions API (5) T09 Entry screen (5) T10 Transaction list (3) T11 Acceptance testing (2) | T03 Design system (5) - Reda T04 Entry mockups (3) - Reda | T01 GitHub repository (3) T02 React Native project (3) T05 Database schema (3) |

Total Done: 9 SP - burndown slightly behind, no alert (gap ≤ 10%).

## 9.5 Expected Results at the End of Sprint 1

- An installable mobile Increment with sign-up, login and manual transaction entry.

- A documented design system and mockups validated by Salma.

- A measured velocity (target: 38 to 42 SP) to serve as a reference for Sprint 2.

- An up-to-date impediment register and a retrospective producing at least two improvement actions.

# 10. Conclusion

This report defined a complete execution plan for the Flousy project, based on Scrum principles. Task delegation relies on explicit criteria (skills, workload, learning) and strict accountability rules. Communication is structured by channel and frequency, the Daily Stand-up ensures daily synchronization, and the burndown, Kanban and velocity provide objective visibility on progress. The four-level escalation process guarantees that no problem goes unanswered, while adaptive planning makes it possible to react to unforeseen events without sacrificing the Sprint Goal.

Several key success factors emerge: transparency (report blockers early), discipline (respect time-boxes and the Definition of Done), clear accountability (one owner per task), flexibility (negotiate scope, not the goal) and continuous improvement through retrospectives.

The next steps concern Sprint 2 (January 19 to 30), focused on the budget engine and alerts. The team will apply the same execution mechanics, enriched by Sprint 1's actual velocity and the actions decided in the retrospective.

# Appendices

## Appendix A: Daily Stand-up Template

| Field | To fill in |
| --- | --- |
| Date / Sprint day | Jan 8, 2026 / Sprint 1, Day 4 |
| Present / Absent | All present (Salma, Youssef, Omar, Nada, Reda) |
| Remaining Story Points (ideal / actual) | 28 / 31 |
| Omar: yesterday / today / blocker | Yesterday: Finished React Native navigation (T02). Today: Starting login screens (T07). Blocker: Waiting for final mockups from Reda. |
| Nada: yesterday / today / blocker | Yesterday: Validated database schema (T05). Today: Starting authentication API (T06). Blocker: Integration test failing on local environment. |
| Reda: yesterday / today / blocker | Yesterday: Design system 80% complete (T03). Today: Finalizing entry mockups (T04) to deliver to Omar by noon. Blocker: None. |
| New impediments (ID, owner) | IMP-02: Integration test failing (Owner: Nada). |
| Decisions and post-Daily actions | Omar and Reda to sync on mockups at 10:00. Omar and Nada to pair-program on the failing test. Youssef to update the burndown chart. |
| Actual Daily duration | 14 min |

## Appendix B: Escalation Ticket Template

| Field | To fill in |
| --- | --- |
| Ticket number | ESC-001 |
| Problem | React Native navigation library incompatible with current framework version, blocking front-end development. |
| Impact (tasks, Sprint Goal) | Blocks tasks T02, T07, and T09. Threatens Sprint 1 Goal (manual entry screen). Delay of 2 days. |
| Current level (1 to 4) | Level 2 |
| Actions already tried | L1: Omar and Nada tested 3 alternative versions of the library for 24h. L2: Youssef consulted documentation, GitHub issues, and community forums. |
| Decision | Downgrade the library to a stable previous version (v5) and implement a custom wrapper to maintain functionality. |
| Owner of implementation | Youssef (for arbitration) & Omar (for code implementation). |
| Date reported / closed | Reported: Jan 6, 2026 / Closed: Jan 8, 2026 |

## Appendix C: Sprint 1 Burndown Chart

Remaining Story Points

40 |  #     *     *

36 |        o           *

32 |              o           *

28 |                    o           *

24 |                          o           *

20 |                                o           *

16 |                                      o           *

12 |                                            o

8 |                                                  o     *

4 |                                                        o     *

0 |  _     _     _     _     _     _     _     _     _     _     o

+------------------------------------------------------------------

0     1     2     3     4     5     6     7     8     9     10    Days (D0 = Jan 5)

Legend :  o = ideal line (40 SP -> 0)   * = actual line   # = ideal and actual overlap

Illustrative data to be replaced by actual values [TO COMPLETE]

## Appendix D: Communication Flow Chart

+--------------------------------------+

|        SUPERVISING PROFESSOR         |

|  Stakeholders (Level 4 escalation)   |

+--------------------------------------+

|

|  Sprint Review / final decisions

v

+----------------------------+                  +----------------------------+

|   Salma - Product Owner    |<--- priorities --->|   Youssef - Scrum Master   |

|Vision, priorities, backlog |<--- arbitration --->| Facilitation, impediments  |

+----------------------------+                  +----------------------------+

|                                               |

|                                               |

v                                               v

+----------------------------------------------------------------------------+

|                     DEVELOPMENT TEAM (self-organizing)                     |

|           Omar (Front-end)  -  Nada (Back-end)  -  Reda (UX/UI)            |

+----------------------------------------------------------------------------+

|

|  Daily Stand-up 9:30 + Kanban + Slack

v

+----------------------------------------------------------------------------+

| CHANNELS: Slack (daily) | GitHub (code) | Trello (tasks) | Email (formal)  |

+----------------------------------------------------------------------------+

## Appendix E: Complete Sprint 1 RACI Matrix

| Task | Salma (PO) | Youssef (SM) | Omar | Nada | Reda |
| --- | --- | --- | --- | --- | --- |
| T01 GitHub repository + CI | I | I | C | R | I |
| T02 React Native project | I | I | R | C | I |
| T03 Design system | A | I | C | I | R |
| T04 Entry mockups | A | I | C | I | R |
| T05 Database schema | C | I | C | R | I |
| T06 Authentication API | A | I | C | R | I |
| T07 Login screens | A | I | R | C | C |
| T08 Transactions API | A | I | C | R | I |
| T09 Entry screen | A | I | R | C | C |
| T10 Transaction list | A | I | R | C | C |
| T11 Testing and acceptance | A | R | C | C | C |

R = Responsible, A = Approver, C = Consulted, I = Informed. Developers' approval is obtained through cross-review.